TrustRent

12-Week Implementation Plan

Smart contracts and backend track, with frontend hand-offs

Course BTCS706N, SVIIT. Based on: TrustRent SRS v1.0, the project synopsis, and the course project timeline. Version 1.0, 21 October 2026.

# 1. Purpose, roles and how to use this plan

This plan turns the approved SRS into 12 weeks of work. It follows the course timeline (UML first, then implementation, CI/CD, testing and deployment) but lets coding start in Week 1, so that diagrams are checked against working code. The diagrams are worth 30% of the grade and must match the final code.

| Track | Who and what |
| --- | --- |
| Blockchain and backend (your track) | Solidity contracts (factory, vault, registries, mock token), Hardhat tests and deployment to Polygon Amoy, the FastAPI (Python) API, PostgreSQL, hashing, encrypted storage, mock identity service, keeper job, account-abstraction integration, subgraph (indexer), and the CI pipeline for these parts. |
| Frontend team | React dashboards for tenant, landlord and arbitrator, social-login screens, calling the API, the indexer and the account-abstraction SDK. They depend on your hand-offs in Section 6. |
| Shared | Jira, Git workflow, UML diagrams, weekly progress reports, README, test chapter, the implementation paper, demo. |

Stack note. This plan follows the SRS and synopsis, updated to a FastAPI backend: Python with FastAPI, PostgreSQL and Pytest.

Calendar note. Week 1 is the first sprint week; dates are left to you. If your final submission is earlier than 12 weeks away, use the priority order in Section 11 to decide what to cut.

# 2. Architecture

Figure 1. TrustRent system architecture and ownership.

## 2.1 What lives where

| Concern | Design |
| --- | --- |
| Source of truth | The chain holds funds, tenancy state, lease and evidence hashes, claims and decisions. The indexer and API only read it. PostgreSQL stores users, metadata and file references. |
| Off-chain files | Lease and evidence files are encrypted by the backend (AES-256-GCM, a random key per file wrapped with a master key from environment configuration), stored behind a StorageProvider interface (IPFS pinning or local encrypted), and referenced by CID. Only hashes go on-chain. |
| Hashing | keccak256, which is native to Solidity and also available in web3.py (backend) and ethers (frontend). A lease hash is the hash of the lease file. Evidence uses a manifest (a JSON list of file hashes, types and timestamps) whose hash is recorded on-chain, so one transaction anchors many files. |
| Identity | Mock verification in the backend. On success, the backend signer (attester role) writes a hash or flag to IdentityRegistry for the user's smart-account address. No personal data on-chain. |
| Gasless use | Social login creates a smart account (ERC-4337). The frontend sends user operations; a bundler and paymaster submit them with gas sponsored. The paymaster policy allows only TrustRent contract calls (FR-7.5). |
| Automatic refund | A contract cannot run on a timer. The vault exposes finalizeRefund(), callable by anyone once the claim window has passed with no claim. The backend keeper job calls it automatically, and the UI offers it as a fallback, so no landlord action is needed. |
| Dashboards | The frontend reads tenancy state from the indexer (GraphQL) and metadata from the API, so the browser never polls the chain. |

## 2.2 Design patterns and where they appear

| Pattern | Contracts | Backend |
| --- | --- | --- |
| Factory | TenancyFactory creates a vault per tenancy (EIP-1167 minimal proxy clones, for low deployment gas, NFR-P-3) | n/a |
| State | Vault behavior guarded by the tenancy state (Drafted, Signed, Active, MoveOut, Disputed, Refunded); invalid transitions revert | Tenancy status model mirrors the same states |
| Strategy | n/a (cap check is a vault rule) | StorageProvider (IPFS or local encrypted); CapPolicy (hard cap versus soft legal warning) |
| Observer | Events emitted on every transition | Indexer and keeper subscribe to events |
| Inheritance | Vault extends OpenZeppelin base contracts | User base class with Tenant, Landlord, Arbitrator subclasses; private fields with getters |

# 3. Tech stack

| Layer | Choice | Owner | Notes |
| --- | --- | --- | --- |
| Contracts | Solidity 0.8.x, OpenZeppelin (Ownable/AccessControl, ReentrancyGuard, SafeERC20, Clones) | You | Custom errors, checks-effects-interactions, no admin withdraw |
| Contract tooling | Hardhat with TypeScript, Chai, hardhat-gas-reporter, solidity-coverage, TypeChain | You | TypeChain gives the frontend typed ABIs |
| Static analysis | Solhint, Slither | You | Run in CI from Week 4, deeper pass in Week 9 |
| Network | Polygon Amoy (EVM test network) | You | Faucet tokens only; verify contracts on the block explorer |
| Backend | Python 3.12, FastAPI, Pydantic validation, structlog logging | You | OpenAPI spec generated and served |
| Database | PostgreSQL with SQLAlchemy 2.0 and Alembic (migrations) | You | Docker Compose locally, free-tier cloud for staging |
| Chain access | web3.py (backend), viem or ethers (frontend) | You / FE | RPC provider with free tier |
| Account abstraction | ERC-4337 bundler and paymaster, with a social-login and smart-account SDK | You + FE | Choose in the Week 2 spike (see Section 10) |
| Indexer | The Graph subgraph (Subgraph Studio). Fallback: Python event listener into PostgreSQL | You | The Polygon docs list Amoy as supported by The Graph |
| Off-chain storage | IPFS pinning service (for example Pinata) behind StorageProvider; local encrypted provider for tests | You | Encrypt before upload |
| Backend tests | Pytest, FastAPI TestClient (httpx), local Hardhat node for integration tests | You | Target set in Section 8 |
| Frontend | React with Vite and TypeScript, GraphQL client, AA SDK | FE | Uses your published ABIs, OpenAPI and subgraph schema |
| CI/CD | GitHub Actions: lint, tests, coverage, gas report, deploy to staging | You + FE | Branch protection on develop and main |
| Hosting | Render (API and keeper), Vercel (frontend), Subgraph Studio, free-tier PostgreSQL | Shared | Free-tier limits are a constraint (SRS 2.5) |
| Project management | Jira (6 two-week sprints), Git feature branches, pull requests with review | Shared | Every commit message carries a Jira ID |

# 4. Smart contract design

## 4.1 Contracts

| Contract | Responsibility |
| --- | --- |
| MockINR | ERC-20 test token standing in for rupees; capped faucet mint so test users can fund deposits. |
| IdentityRegistry | attest(user, attestationHash) by the attester role (backend signer); revoke; isVerified(user). No personal data. |
| ArbitratorRegistry | Owner approves or removes arbitrators; isApproved(address). |
| TenancyFactory | createTenancy(...) checks that both parties are verified, cap is at most the deposit and the claim window is in range, then clones and initializes a vault; emits TenancyCreated. |
| DepositVault | One per tenancy. Holds the deposit, enforces the state machine, cap, claim window, refund and arbitrator decision (details below). |

## 4.2 Vault interface (first draft for the frontend)

| Function | Caller | From state | Effect |
| --- | --- | --- | --- |
| sign() | Landlord, tenant | Drafted | Records each signature; when both have signed, state becomes Signed |
| lockDeposit() | Tenant | Signed | Pulls the exact deposit in MockINR; once only |
| recordEvidence(type, hash) | Landlord, tenant | Signed (move-in), Active/MoveOut (move-out) | Stores hash, submitter and timestamp; immutable. Signed becomes Active when the deposit is locked and a move-in hash exists |
| startMoveOut(hash) | Landlord, tenant | Active, after lease end | Records move-out evidence; state MoveOut; claim deadline = now + window |
| raiseClaim(amount, evidenceRefs) | Landlord | MoveOut, within window | Reverts if amount is above cap or evidence is missing; state Disputed; funds stay locked |
| finalizeRefund() | Anyone | MoveOut, window passed, no claim | Returns the full deposit to the tenant; state Refunded |
| assignArbitrator(addr) | Registry admin | Disputed | Assigns an approved arbitrator (method: see decisions, Section 8) |
| decide(landlordAmt, tenantAmt) | Assigned arbitrator | Disputed | Reverts unless amounts sum to the deposit and landlord amount is within cap; pays both; state Refunded |

Events (the frontend and indexer depend on these): TenancyCreated, LeaseSigned, DepositLocked, EvidenceRecorded(type, hash, by, timestamp), MoveOutStarted(deadline), ClaimRaised(amount), ArbitratorAssigned, DecisionMade(arbitrator, landlordAmount, tenantAmount), Refunded(to, amount), StateChanged(from, to).

Invariants to test (NFR-S-1 to S-4, BR-1 to BR-8): payouts always sum to the deposit; no state with funds lacks a path to Refunded; only legal transitions succeed; lease terms and recorded hashes never change after signing; no function lets one party withdraw the deposit alone.

Security checklist: reentrancy guard on every payout, SafeERC20, role checks on every function, custom errors for clear messages, timestamps used only for windows (not randomness), no upgradeable or admin-withdraw paths, secrets never committed.

# 5. Backend design

## 5.1 Modules and classes

- Domain classes: User (base) with Tenant, Landlord, Arbitrator; private attributes exposed through properties, with validation.

- Services: AuthService, IdentityService (mock), TenancyService, EvidenceService, HashService, KeeperService, ChainClient (web3.py wrapper).

- Interfaces: StorageProvider (IPFS, local encrypted), CapPolicy, IdentityProvider (mock now, real provider later).

- Layers: routers, services, repositories (SQLAlchemy), chain, storage. Routers contain no business logic.

## 5.2 REST API (first draft)

| Endpoint | Role | Purpose |
| --- | --- | --- |
| POST /auth/login | Any | Exchange the social-login token for a session JWT; create the user and record the smart-account address |
| GET /me | Any | Profile, role, verification status |
| POST /identity/verify | User | Mock verification; on success the backend attests on-chain |
| POST /tenancies/draft | Landlord | Upload lease and terms; returns leaseHash, CID and the parameters for the on-chain createTenancy |
| GET /tenancies, GET /tenancies/:id | Parties | Metadata merged with indexer state |
| POST /tenancies/:id/evidence | Parties | Upload files; returns the manifest hash to record on-chain |
| GET /evidence/:id/verify | Parties, arbitrator | Recompute the hash and compare with the on-chain value (match or mismatch) |
| GET /evidence/:id/file | Parties, assigned arbitrator | Access-controlled decrypted download |
| GET /arbitrator/disputes (and /:id) | Arbitrator | Assigned disputes with claim, terms and evidence status |
| POST /faucet | User (testnet only) | Mint MockINR for demos |

Keeper job: runs on a schedule, finds tenancies whose claim window has passed with no claim, and submits a sponsored finalizeRefund(). It is idempotent and logs every attempt.

Data entities (SRS B.4): User, Tenancy, Evidence, Claim, Decision, and the attestation and arbitrator registry entries. Chain and indexer remain the source of truth for state and funds.

# 6. Frontend hand-offs (what you publish, and when)

| Week | Artifact for the frontend team |
| --- | --- |
| 2 | OpenAPI draft and a mock API server (so screens can be built before the backend exists) |
| 3 | Contracts package v0.1: TypeChain types, ABIs and addresses.json for Amoy |
| 5 | Error-code catalog (contract errors and API errors mapped to plain-language messages) |
| 6 | State and action matrix (below) confirmed; arbitrator endpoints |
| 7 | Interface freeze v1.0: ABIs, OpenAPI, subgraph GraphQL schema and endpoint, error catalog |
| 8 on | Breaking changes only through a pull request that updates the interface docs, announced to the team |

State and action matrix (each screen shows the current state and the actions available to the current user):

| State | Tenant | Landlord | Arbitrator |
| --- | --- | --- | --- |
| Drafted | Review lease, sign | Create, upload lease, sign | None |
| Signed | Lock deposit, add move-in evidence | Add move-in evidence | None |
| Active | View, add evidence | View, add evidence | None |
| MoveOut | Add evidence, view claim window; trigger refund after window | Add evidence, raise capped claim within window | None |
| Disputed | View claim and evidence | View claim and evidence | Review evidence, decide split |
| Refunded | View history | View history | View decision |

# 7. The 12-week plan

Course timeline phases are shown with each week. Sprints are two weeks each (Sprint 1 is Weeks 1 and 2, and so on). Every week ends with a weekly progress report and a short demo to the team. Commit messages carry Jira IDs and every change goes through a reviewed pull request.

| Weeks | Focus | Milestone |
| --- | --- | --- |
| 1-2 | Setup, functional modeling, identity, account-abstraction spike | Contract deployed on Amoy; gasless transaction demo (or fallback decided) |
| 3-4 | Object-oriented analysis, tenancy creation, deposit, evidence, full CI | Tenancy reaches Active on Amoy; CI blocks failing pull requests |
| 5-6 | Interaction modeling, move-out, claims, refund, arbitration, class design | Happy path and disputed path both work end to end |
| 7-8 | System architecture, indexer, interface freeze, integration | Teammate runs both paths through the UI |
| 9-10 | Security, CI/CD hardening, scenario testing, feature freeze | All scenarios pass on staging |
| 11-12 | Evaluation, deployment, report, demo | Live demo URL; evaluation numbers frozen |

Week 1: Initiation and foundations (Sprint 1; course Phase 1)

| Contracts | Hardhat TypeScript project; OpenZeppelin; MockINR with capped faucet; TenancyState enum and vault skeleton with state guards; first tests for valid and invalid transitions; deploy script to local node and Amoy; wallet and key hygiene (.env, never commit). |
| --- | --- |
| Backend | FastAPI skeleton with a virtual environment and locked dependencies; PostgreSQL in Docker Compose; SQLAlchemy models and first Alembic migration (users, tenancies); config loader (Pydantic settings); health endpoint; Ruff linting and formatting; Pytest set up. |
| Frontend and shared | Jira with six sprints and epics; GitHub repository with main and develop, branch protection, pull request template, commit format (TR-12: message); frontend scaffold (React, Vite); agree the API-first workflow. |
| Docs | Vision document and product backlog (from synopsis and SRS); weekly report 1; decision meeting on the open items in Section 8. |
| Exit criteria | Contract address on Amoy; backend and contracts each have one passing test; open items TBD-1 to TBD-4 decided. |

Week 2: Functional modeling, identity and account abstraction (Sprint 1; course Phase 1)

| Contracts | IdentityRegistry (attester role, attest, revoke, isVerified) and ArbitratorRegistry (approve, remove, isApproved) with tests. Account-abstraction spike (1 to 2 days): compare bundler and paymaster providers for Amoy support, free testnet sponsorship and social login; build "hello gasless": social login, smart account, sponsored call. |
| --- | --- |
| Backend | Auth module (verify social-login token, issue session JWT), /me; mock IdentityService and /identity/verify that attests on-chain through the backend signer; minimal GitHub Actions (lint and tests on pull requests to develop). |
| Frontend and shared | Wireframes for three dashboards; login screen with the chosen SDK; mock API server from your OpenAPI draft. |
| Docs | Use case diagram and descriptions (UC-1 to UC-8, SRS B.2); map use cases to Jira stories; weekly report 2. |
| Exit criteria | Sponsored transaction works on Amoy, or the fallback (plain signing first) is documented and agreed; a verified user can be attested. |

Week 3: Static analysis; tenancy creation and lease anchoring (Sprint 2; course Phase 2)

| Contracts | TenancyFactory with EIP-1167 clones and vault initialize(); createTenancy in Drafted with checks (both verified, cap at most deposit, window in range); sign() by each party, then Signed; immutability after signing; events and custom errors; negative tests (unverified, wrong caller, double sign). |
| --- | --- |
| Backend | StorageProvider interface with LocalEncrypted (AES-256-GCM) and IPFS providers; HashService (keccak256); POST /tenancies/draft (upload, hash, encrypt, store, return parameters); GET /tenancies; lease verification endpoint (FR-2.6). |
| Frontend and shared | Create-tenancy form and lease review screen against the mock API; publish contracts package v0.1. |
| Docs | Object diagram and domain class diagram (SRS B.4 entities); weekly report 3; implementation paper: introduction and methodology outline. |
| Exit criteria | Drafted to Signed works end to end on Amoy through the API. |

Week 4: Dynamic analysis; deposit, move-in evidence, full CI (Sprint 2; course Phase 2)

| Contracts | lockDeposit (SafeERC20, tenant only, exact amount, once); recordEvidence for move-in; Signed to Active guard (deposit locked and move-in hash present); batching approve and lock in one user operation if the provider supports it; gas reporter on. |
| --- | --- |
| Backend | Evidence upload (per-file hash, manifest, manifest hash, encrypted storage, database rows); GET /evidence/:id/verify; access-control middleware (parties only). |
| CI and shared | Full pipeline: contract tests with coverage and gas report, backend tests, lint, Solhint; required status check on develop; frontend wiring for deposit and evidence upload; weekly report 4. |
| Docs | Activity diagram with swimlanes (tenant, landlord, arbitrator, system) and the state-machine diagram (SRS B.1). |
| Exit criteria | Tenancy reaches Active on Amoy; a deliberately failing pull request is blocked by CI (keep the screenshot as rubric evidence). |

Week 5: Interaction modeling; move-out, claims, automatic refund (Sprint 3; course Phase 3)

| Contracts | startMoveOut (after lease end, with move-out hash) opens the claim window; raiseClaim (landlord, within window, at most cap, evidence present) moves to Disputed; finalizeRefund() for anyone after the window with no claim. Hardhat time-travel tests on every boundary (start, last second, exact deadline). |
| --- | --- |
| Backend | KeeperService scans for elapsed windows and submits sponsored finalizeRefund(), idempotent and logged; claim read endpoints; error-code catalog mapping contract errors to plain messages (FR-7.4). |
| Frontend and shared | Move-out, claim and claim-response screens; status timeline with claim-window countdown (FR-8.5). |
| Docs | Sequence diagrams from real method calls: create and sign; lock deposit and evidence; claim and automatic refund; weekly report 5. |
| Exit criteria | Full happy path (no dispute) passes in tests and on Amoy, including a keeper-triggered refund. |

Week 6: Detailed class design; arbitration (Sprint 3; course Phase 3)

| Contracts | Arbitrator assignment (prototype: registry admin assigns an approved arbitrator); decide() with all validations; payouts with checks-effects-interactions and ReentrancyGuard; optional acceptClaim() for the tenant; design of an arbitrator-inactivity fallback (decision in Section 8); complete negative tests (unauthorized, double decision, wrong sums, over cap). |
| --- | --- |
| Backend | Arbitrator endpoints and evidence access for the assigned arbitrator only; hash re-verification in the arbitrator view; admin script to approve arbitrators; refactor to the OO design (User hierarchy, services, CapPolicy strategy). |
| Frontend and shared | Arbitrator dashboard and decision form. |
| Docs | Detailed class diagram (contracts and backend) and package diagram (matches the folder structure); weekly report 6; implementation paper: methodology sections. |
| Exit criteria | Disputed path works end to end locally and on Amoy; a table mapping each pattern (Factory, State, Strategy, Observer) to its code location. |

Week 7: System architecture; indexer; interface freeze (Sprint 4; course Phase 3)

| Contracts | Verify contracts on the Amoy explorer; finalize events; first gas optimization pass (storage packing, custom errors, clones); paymaster policy allowing only TrustRent contracts and selectors, with per-user limits (FR-7.5). |
| --- | --- |
| Backend and indexer | Subgraph schema (Tenancy, Evidence, Claim, Decision, Transition), mappings, deploy to Subgraph Studio on Amoy; fallback listener ready if indexing is unreliable; publish interface v1.0 (ABIs, OpenAPI, GraphQL schema, error catalog, state and action matrix). |
| Frontend and shared | Dashboards read from indexer and API on staging; remove the mock server. |
| Docs | Component diagram and planned deployment diagram; architecture section of the report; weekly report 7. |
| Exit criteria | Dashboard shows a new on-chain event within about 30 seconds (NFR-P-2). |

Week 8: Integration sprint (Sprint 4; course Phase 4)

| Contracts | Fix integration findings; reproducible deploy script (deploy:amoy writes addresses.json); close review comments. |
| --- | --- |
| Backend | Pydantic validation on every route, rate limiting, security headers, role checks on every route (NFR-SEC-1), audit log, secrets only in environment, migrations; raise Pytest coverage; serve OpenAPI docs. |
| Frontend and shared | Real UI flow with social login and sponsored operations; error and retry states (FR-7.4); code review rotation across the team. |
| Process | All core-feature stories Done or in final review (guide rule); weekly report 8. |
| Exit criteria | A teammate (not you) completes one happy tenancy and one disputed tenancy through the UI. |

Week 9: Security and CI/CD hardening (Sprint 5; course Phase 4)

| Contracts | Slither pass and fixes; fuzz and invariant tests (payouts sum to deposit, no stuck funds, only legal transitions); checklist review (reentrancy, access control, timestamps, ERC-20 return values); gas optimization pass 2. |
| --- | --- |
| Backend | FastAPI TestClient integration tests with a local Hardhat node and test database; keeper tests; dependency audit. |
| CI/CD | Auto-deploy API to Render and frontend to Vercel from develop (staging); test and coverage reports in the pipeline; build badge in the README; confirm the pipeline blocks merge on failing tests. |
| Docs | README (setup, environment variables, run, test, deploy); weekly report 9; implementation paper: implementation section. |
| Exit criteria | Green pipeline from a clean clone; security checklist completed and recorded. |

Week 10: Scenario testing; feature freeze (Sprint 5; course Phase 4)

| Scenarios | S1 happy refund via keeper; S2 claim then arbitrator decision; S3 cap violation; S4 unauthorized caller; S5 claim outside window; S6 tampered evidence shows hash mismatch; S7 unverified user blocked. Scripted so they can be rerun. |
| --- | --- |
| Backend and contracts | Fix findings; resolve remaining open items and record them in SRS v1.1 change log; basic concurrency check for a few simultaneous tenancies (NFR-P-4). |
| Frontend and shared | UX polish, in-app help text, user guide with screenshots. |
| Process | Feature freeze at the end of the week; Jira: every story Done or explicitly deferred; weekly report 10. |
| Exit criteria | All seven scenarios pass on staging Amoy. |

Week 11: Testing and evaluation (Sprint 6; course Phase 5)

| Contracts | Final gas table per function (create, sign, lock, evidence, claim, decide, refund) and clones versus full deployment; coverage report; list of negative tests. |
| --- | --- |
| Backend | API latency (median and 95th percentile), event-to-dashboard latency, coverage report; fix-only changes from now on. |
| Docs | Testing chapter; implementation paper: experiments and results with screenshots; weekly report 11. |
| Exit criteria | Evaluation numbers frozen and reproducible with one command. |

Week 12: Deployment, final review and demo (Sprint 6; course Phase 5)

| All | Final deployment to Amoy with verified contracts and production environment; final deployment diagram matches what is live; README final; live demo URL; demo rehearsal including a fallback (pre-seeded tenancy and a recorded video); handover. |
| --- | --- |
| Docs | Final report compiled; final weekly report signed off by the project guide; both papers finalized. |
| Exit criteria | Full demo from the live URL, from lease signing to refund, including a disputed case. |

# 8. Open items from the SRS, with proposed defaults

These are proposals for the team and guide to confirm, not decisions. Decide TBD-1 to TBD-4 in Week 1, the rest by Week 6.

| Item | Question | Proposed default |
| --- | --- | --- |
| TBD-1 | Claim window length | 7 days default; lease may set between 3 and 30 days |
| TBD-2 | Cap: hard legal limit or lease parameter? | Contract enforces cap at most the deposit; the backend warns (soft) if deposit exceeds two months' rent |
| TBD-3 | Can the tenant accept a claim directly? | Yes: acceptClaim() in Disputed settles immediately; otherwise the arbitrator decides |
| TBD-4 | How is an arbitrator assigned? | Registry admin assigns from approved arbitrators in the prototype; random or agreed assignment as future work |
| TBD-5 | Arbitrator fees | None in the prototype; list as future work |
| TBD-6 | Mock identity fields | Name, phone, ID type and a fake ID number; rule-based result with a short delay; attestation is a hash of user id and timestamp |
| TBD-7 | Hash and evidence format | keccak256 and a JSON manifest; images and PDF up to 10 MB each |
| TBD-8 | Token lifetime, sponsorship limits | 1 hour access token with refresh; paymaster allowlist of TrustRent contracts and a daily per-user limit |
| TBD-9 | Quantitative targets | Contract coverage at least 90%, backend at least 70%; API 95th percentile within 3 s; event latency within 30 s |
| TBD-10 | Data protection | Data minimization, encrypted storage, no personal data on-chain; legal review is out of scope |
| TBD-11 | Arbitrator inaction, early termination | Fallback after a long timeout (for example 30 days) returns the full deposit to the tenant; early termination and extension out of scope |

# 9. Testing and evaluation plan

- Contracts (Hardhat): unit tests for every transition and guard, negative tests for NFR-SEC-5, time-travel tests for window boundaries, invariant tests, gas report per function.

- Backend (Pytest and FastAPI TestClient): unit tests for services and hashing, integration tests against a local Hardhat node and a test database, keeper tests.

- End to end: the seven scripted scenarios in Week 10, run on staging Amoy.

- Evaluation results for the implementation paper: gas cost per operation, coverage, API and event latency, and one complete tenancy including a dispute.

# 10. Risks and fallbacks

| Risk | Mitigation |
| --- | --- |
| Account abstraction takes longer than planned | Do the Week 2 spike early. Candidate providers include Pimlico, Alchemy, Particle, ZeroDev and Biconomy. Check each for Amoy support, free testnet sponsorship and a social-login option before choosing; I did not verify these terms. Fallback: build and demo with plain signing, and add sponsorship when ready. |
| Indexer unreliable or delayed on Amoy | The Graph's Polygon documentation lists Amoy as supported, but publishing to the network involves extra steps. Keep the Python event-listener fallback ready in Week 7. |
| Free-tier limits (RPC, hosting, pinning) | Cache reads in PostgreSQL, keep a local Hardhat setup for development, and deploy to Amoy only at milestones. |
| Automatic refund needs a transaction | Keeper job plus a user-triggered fallback button; anyone may call finalizeRefund(). |
| Key management | Separate keys for deployer, attester and paymaster; only in environment configuration; rotate if exposed. |
| Interface drift between teams | Freeze interface in Week 7; changes only through pull requests that update the interface docs. |
| Diagrams drift from code | Review diagrams against code at the end of each sprint; update diagrams in the same pull request as structural changes. |
| Late discovery of a design flaw | Two end-to-end paths run by Week 6 and integration in Weeks 7 and 8, leaving time to fix before the freeze. |

# 11. If time is short: priority order

Build in this order and cut from the bottom:

1. Vault, state machine and tests (the core of the project).

2. Evidence hashing, claims, automatic refund and arbitrator decision.

3. Backend: authentication, mock identity, hashing and encrypted storage.

4. Indexer for live dashboards (use the Python listener if needed).

5. Gasless, wallet-free onboarding (SRS marks it High, so agree any cut with your guide).